## Summary
Metric | Value
Total Records | 348
Active Locations | 4
Activity Categories | 6
Tracked Activities | 24
Project Start Date | 2026-01-27
Project End Date | 2026-04-30
Project Duration (Days) | 93
Total Project Cost (₦) | ₦4,487,370.00
Total Labour Cost (₦) | ₦744,500.00
Total Equipment Hours | 396.00
Total Excavation (m) | 1,012.30
Average Excavation Rate (₦/m) | ₦0.00
Cement Delivered (Bags) | 950
Cement Used (Bags) | 909
Cement Missing (Bags) | 36
Cement Spillage (Bags) | 1
Cement Remaining (Bags) | 4